## Sheet1
To do list for IoT Team Base on LoRa Communication (1 Month only)
Date | Task | Key Response | Deadline | Percentage of Finish | Comment
Week 1 | Tranfer Data from LoRa Node Sensor to Gateway | Ponareay, Chailin, Rina | 2023-12-07
2023-12-01 | Testing Gateway with GPRS + Wifi | Ponareay | 2023-12-07
2023-12-02 | Testing LoRa Sending Data with Serial Monitor | Ponareay | 2023-12-07
2023-12-03 | Draw Schematic of Lora Node Sensor | Chailin | 2023-12-07
2023-12-04 | Draw PCB of LoRa Node Sensor | Chailin | 2023-12-07
2023-12-05 | Testing on Transfering Data from Sensor to Gateway | Ponareay, Chailin | 2023-12-07
2023-12-06 | Testing on Transfering Data from Sensor to Gateway | Ponareay, Chailin | 2023-12-07
2023-12-07 | Testing on Transfering Data from Sensor to Gateway | Ponareay, Chailin | 2023-12-07
Week 2 | MQTT Real Time Database | Ponareay, Chailin, Rina | 2023-12-14
2023-12-08 | Research on How to connect the Firebase with ESP32 | Rina | 2023-12-14
2023-12-09 | Getting Communnicate with LoRa and Gateway on Real time Data | Rina, Ponareay | 2023-12-14
2023-12-10 | Control the Data | Ponareay, Rina | 2023-12-14
2023-12-11 | Implement on How to store and Stream Data | Ponareay, Chailin, Rina | 2023-12-14
2023-12-12 | Implement on How to store and Stream Data | Ponareay, Chailin, Rina | 2023-12-14
2023-12-13 | Implement on How to store and Stream Data | Ponareay, Chailin, Rina | 2023-12-14
2023-12-14 | Implement on How to store and Stream Data | Ponareay, Chailin, Rina | 2023-12-14
Week 3 | Design New LoRa Node PCB Board + Show all the Data on Web Interface | Ponareay, Chailin, Rina | 2023-12-21
45275 | Prototype on Print Circuit Board for LoRa Sensor | Chailin | 2023-12-21
2024-12-16 | Assembly the Component | Chailin | 2023-12-21
2023-12-17 | Check the Board Quality | Ponareay, Prof | 2023-12-21
2023-12-18 | Read and Write Data from Sensor to Show in Real Time | Ponareay, Rina | 2023-12-21
2023-12-19 | Read and Write Data from Sensor to Show in Real Time | Ponareay, Rina | 2023-12-21
2023-12-20 | Read and Write Data from Sensor to Show in Real Time | Ponareay, Rina | 2023-12-21
2023-12-21 | Read and Write Data from Sensor to Show in Real Time | Ponareay, Rina | 2023-12-21
Week 4 | Design New Web Interface | Ponareay, Chailin, Rina | 2023-12-21
2023-12-22 | Show all the Data in Number and Percentage | Ponareay | 2023-12-30
2023-12-23 | Saving Data for Backup | Ponaray, Chailin, Rina | 2023-12-30
2023-12-24 | Design a new interface (With no AI Yet) | Ponaray, Chailin, Rina | 2023-12-30
2023-12-25 | Design a new interface (With no AI Yet) | Ponaray, Chailin, Rina | 2023-12-30
2023-12-26 | Design a new interface (With no AI Yet) | Ponaray, Chailin, Rina | 2023-12-30
2023-12-27 | Design a new interface (With no AI Yet) | Ponaray, Chailin, Rina | 2023-12-30
2023-12-28 | Design a new interface (With no AI Yet) | Ponaray, Chailin, Rina | 2023-12-30
2023-12-29 | Design a new interface (With no AI Yet) | Ponaray, Chailin, Rina | 2023-12-30
2023-12-30 | Design a new interface (With no AI Yet) | Ponaray, Chailin, Rina | 2023-12-30
Prof: | Seven, Bora
Student | Ponareay
Chailin
Rina